## Sheet1
Note: 1 - Download the matrix to your local PC and study all the Attributes (Column F). Ensure they may sense to you. If necessary, add/remove/update the attributes. 2 - Assign Yes/No value to each attribute (Column G) 3 - Decide if any attributes in Column F have upstream dependencies on other attributes in Column F. List upstream Attribute # (Column E) in "Dependency on Other Attributes" column? (Column H). Changed pre-populated values as you see fit. 4 - Decide if improving an attribute in best to be done by directly acting towards an attribute OR acting upon its upstream dependency.
Attribute Grouping |  |  |  | Attribute # | Attribute | Attribute Value (Yes/No) | Dependency on Other Attributes? | What trends are being observed over time? For a given attribute? For an upstream attribute?
| Scrum Framework | Scrum Roles | Scrum Master | 1 | Is there SM identified? | N/A | 89-93
|  |  |  | 2 | Is SM democratically elected by Team and embraces the role? | N/A | 89-93
|  |  |  | 3 | Does SM play the role effectively? | N/A | 89-93
|  |  | Product Owner | 4 | Is PO identified? | N/A | 89-93
|  |  |  | 5 | Is PO empowered? | N/A | 7
|  |  |  | 6 | Is PO appropriately engaged with Team? | N/A | 9, 11, 98, 99 ,100
|  |  |  | 7 | Is PO appropriately positioned organizationally? | N/A | 89-93
|  |  |  | 8 | Is PO effectively supported by SMEs/Stakeholders? | N/A | 7
|  |  | Developer(s) | 9 | Is Team/Developers fully dedicated to Scrum? | N/A | 89,90,92
|  |  |  | 10 | Is Team co-located? | N/A | 93-95
|  |  |  | 11 | Is Team/Developers cross-functional (T-shaped)? | N/A | 93-95
|  |  |  | 12 | Is there swarming and cross-pollination with knowledge? | N/A | 93-95
|  | Scrum Events | Sprint Planning | 13 | Is the event regularly held? | N/A | likely independent
|  |  |  | 14 | Is PO in attendance? | N/A | 4,5,6,7,8
|  |  |  | 15 | Is entire Team in attendance? | N/A | 9
|  |  |  | 16 | Does it result in prioritized & 'doable' Sprint Backlog? | N/A | 54
|  |  | Product Backlog Refinement (PBR) | 17 | Is the event regularly held? | N/A | likely independent
|  |  |  | 18 | Is entire Team in attendance? | N/A
|  |  |  | 19 | Is PO in attendance & prioritizing work? | N/A | 4,5,6,7,8
|  |  |  | 20 | Are SMEs/Stakeholders in attendance & clarifying? | N/A | 8
|  |  |  | 21 | Does PBR result in improved understanding of upcoming work? | N/A | 62,63
|  |  | Sprint Review | 22 | Is the event regularly held? | N/A | 3
|  |  |  | 23 | Is real PSPI being reviewed? | N/A | 51,52,53
|  |  |  | 24 | Is entire Team in attendance? | N/A | 9
|  |  |  | 25 | Is PO in attendance & accepting work? | N/A | 4,5,6,7,8
|  |  |  | 26 | Are SMEs/Stakeholders in attendance & giving feedback? | N/A | 8
|  |  |  | 27 | Does the event produce output that will become input into Sprint Retrospective? | N/A | 25,26
|  |  | Sprint Retrospective | 28 | Is the event regularly held? | N/A | likely independent
|  |  |  | 29 | Is entire Team in attendance? | N/A | 9
|  |  |  | 30 | Is it conducted in a safe and trusty environment? | N/A | 94-96
|  |  |  | 31 | Do Team-level action items get resolved, once identified? | N/A | 5,7
|  |  |  | 32 | Do external to Team action items get escalated and resolved timely? | N/A | 5,7
|  |  | Daily Stand Up | 33 | Is the event regularly held? | N/A | 3
|  |  |  | 34 | Is entire Team in attendance? | N/A | 9
|  |  |  | 35 | Is the event's format appropriate and helps Team proceeding through Sprint? | N/A | 3
|  | Scrum Artifacts | Product Backlog (PBL) | 36 | Does the artifact exist? | N/A | 4,5,6,7,8
|  |  |  | 37 | Is it highly visible? | N/A | 4,5,6,7,8
|  |  |  | 38 | Is it prioritized? | N/A | 4,5,6,7,8
|  |  |  | 39 | Is it estimated? | N/A | 17-20
|  |  |  | 40 | Is it continuously refined? | N/A | 17-20
|  |  |  | 41 | Is it treated as a single source of prioritized Team work? | N/A | 8,9,10
|  |  | Sprint Backlog | 42 | Does the artifact exist (based on DoR)? | N/A | 58
|  |  |  | 43 | Is it clearly defined at the beginning of each sprint? | N/A | 4,5,6,7,8
|  |  |  | 44 | Does it reflect priorities of PBL? | N/A | 4,5,6,7,8
|  |  |  | 45 | Is it supportive of sprint vision? | N/A | 4,5,6,7,8
|  |  |  | 46 | Is sprint scope protected? | N/A | 3
|  |  | Product Increment (PSPI) | 47 | Does it get delivered at the end of every Sprint? | N/A | 49
|  |  |  | 48 | Does it meet Acceptance Criteria? | N/A | 4,5,6,7,8
|  |  |  | 49 | Does it meet DoD? | N/A | 59, 83-88
|  |  |  | 50 | Does it get delivered to end-customer (production)? | N/A | 49
|  | Scrum Team Dynamics |  | 51 | Is Sprint of appropriate duration (1-4 weeks)? | N/A | likely independent
|  |  |  | 52 | Is Sprint duration chosen by and optimized for Team and its work? | N/A | likely independent
|  |  |  | 53 | Does Sprint duration remain consistent? | N/A | 47
|  |  |  | 54 | Does Definition of Ready (DoR) exist? | N/A | 9,10,11,12
|  |  |  | 55 | Does Definition of Done (DoD) exist? | N/A | 9,10,11,12
|  |  |  | 56 | Is there shared ownership (commitments, deliverables) by Team? | N/A | 93-96, 99,100
|  |  |  | 57 | Is Team size appropriate (3-9)? | N/A | 13-16
|  |  |  | 58 | Is Team co-located? | N/A | 96
|  |  |  | 59 | Is Team's structure flat? | N/A | 92
|  |  |  | 60 | Does Team has all skill set required to work on PBL? | N/A | 15
|  |  |  | 61 | Does Team have hard external dependencies? | N/A | 64
| Agile Transparency & Information Radiation | Strategic Planning |  | 62 | Does Product Owner have Product Vision? | N/A | 9,10,11,12
|  |  |  | 63 | Does Team have clear understanding of Strategic Goals? | N/A | 9,10,11,12
|  |  |  | 64 | Is Scope fixed? | N/A | 9,10,11,12
|  |  |  | 65 | Is Timeline fixed? | N/A | 9,10,11,12
|  |  |  | 66 | Is Budget fixed? | N/A | 9,10,11,12
|  |  |  | 67 | Does Team rely on historical Velocity to forecast PBL completion? | N/A | 69-71
|  |  |  | 68 | Are Release and Epic/Theme Burn Up/Down charts being used? | N/A | 69-71
|  | Agile Metrics/ Reporting | Availability | 69 | Does Team use Sprint Story/Task Board? | N/A | likely independent
|  |  |  | 70 | Does Team use Sprint Burn Up/Down chart? | N/A | 72
|  |  |  | 71 | Does Team rely on average Velocity (trends) to plan next Sprint? | N/A | 72
|  |  | Reliability | 72 | Are Team-level metrics Reliable? | N/A | 46,50
|  |  |  | 73 | Do metrics represent a "free by-product" of healthy Team dynamics? | N/A | 73-75
|  |  | Usage | 74 | Are Team-level metrics effectively used with Product Owner? | N/A | 77
|  |  |  | 75 | Are Team-level metrics properly interpreted at senior level? | N/A | 72,89,90
| Tooling |  |  | 76 | Are tools available? | N/A | likely independent
|  |  |  | 77 | Are tools properly used and increase team efficiency? | N/A | 76
|  |  |  | 78 | Do Teams own tool configuration? | N/A | 76
| Agility at Scale |  |  | 79 | Are scrum scaling frameworks well understood? | N/A | 89,90,92
|  |  |  | 80 | Is appropriate scaling framework selected? | N/A | 79
|  |  |  | 81 | Do teams scale-up Product/Feature-centric work? | N/A | 79
|  |  |  | 82 | Is scaled development effectively supported by Product Owner(s) team? | N/A | 79
| Agile Engineering |  |  | 83 | Continuous Integration/Deployment (CI/CD)? | N/A | likely independent
|  |  |  | 84 | Pair Programming? Swarming? | N/A | likely independent
|  |  |  | 85 | ATDD/TDD? | N/A | likely independent
|  |  |  | 86 | Architecture Ownership? | N/A | likely independent
|  |  |  | 87 | Automatic Testing? | N/A | likely independent
|  |  |  | 88 | Automatic Deployment? | N/A | likely independent
| Organizational Agility at System Level |  |  | 89 | Is leadership properly educated about agility? | N/A | likely independent
|  |  |  | 90 | Is leadership supportive of agility, in it shows in concrete actions? | N/A | 89
|  |  |  | 91 | Is there a trusted and collaborative relationship within an organization? | N/A | 92
|  |  |  | 92 | Is organizational design/structure/hierarchy supportive of agility? | N/A | likely independent
|  |  |  | 93 | Is there a well defined career path for key agile roles? | N/A | 92
|  |  |  | 94 | Is monetary incentives/compensation based on collective performance? | N/A | 95
|  |  |  | 95 | Are HR policies up to modern industry standards(research)? | N/A | 95, 92
|  |  |  | 96 | Are location strategies favorable for collaboration? | N/A | 92

## Sheet2
N/A
Yes | 1
No | 2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100